## Team Backlog
Team Backlog |  |  |  |  | Hacker Kermit
Task Name | Assignee | Task Status | Expected Time to Finish (Hrs) | Actual Time to Finish (Hrs)
Design
High Level Design
Modules' Description | All Team | Done | 4 | 4
Project Circuit Schematic | Hossam | Done | 1 | 2
Drivers' Documentation | All Team | Done | 2
Low Level Design
Functions' Flowchart | All Team | Done | 3 | 4
Summary
Document File | Abdelrhman | Done | 3 | 3
Implementation
MCAL Module
DIO Driver | Hossam | Done | 1 | 1
EXI Driver | Abdelrhman | Done | 3 | 2
TMR Driver | Mahmoud | Done | 1 | 2
I2C Driver | Mahmoud | Done | 4 | 9
SPI Driver | Hossam | Done | 4 | 6
UART Driver | Abdelrhman | Done | 4 | 5
HAL Module
MBTN Driver (Multifunctional button) | Hossam | Done | 2 | 1
BUZ Driver | Abdelrhman | Done | 1 | 1
LCD Driver | Hossam | Done | 1 | 1
KPD Driver | Abdelrhman | Done | 3 | 2
EEPROM Driver | Mahmoud | Done | 3 | 7
APP Module
ATM ECU APP | Hossam | Done | 10 | 7
Card ECU APP | Abdelrhman | Done | 4 | 6
Testing
Documentation
Test Protocol Excel Sheet | All Team | Done | 4 | 6
Unit Testing
Test MCAL | All Team | Done | 3 | 4
Test HAL | All Team | Done | 3 | 6
System Testing
Test APP | All Team | Done | 2 | 3
Final Requirements Review | All Team | Done | 1 | 1
Video
Video Recording | All Team | Done | 1 | 1
Video Editing | Hossam | Done | 1 | 1

## Test Protocol
Test Protocol | [5 empty] | Hacker Kermit
Test Case ID | Test Case Description | Test Case Steps | Expected Result | Actual Result | Pass/Fail
MCAL Module
DIO Driver
TC_DIO_001 | Test DIO initialization | 1. Call DIO_init with valid parameters | EN_DIO_Error_T is returned as DIO_OK | Matches Expected Result | Pass
TC_DIO_002 | Test DIO read | 1. Call DIO_init with valid parameters 2. Call DIO_write with a value of 1 3. Call DIO_read | u8_a_value is returned as 1 | Matches Expected Result | Pass
TC_DIO_003 | Test DIO write | 1. Call DIO_init with valid parameters 2. Call DIO_write with a value of 1 | EN_DIO_Error_T is returned as DIO_OK | Matches Expected Result | Pass
TC_DIO_004 | Test DIO toggle | 1. Call DIO_init with valid parameters 2. Call DIO_write with a value of 1 3. Call DIO_toggle 4. Call DIO_read | u8_a_value is returned as 0 | Matches Expected Result | Pass
TC_DIO_005 | Test port initialization | 1. Call DIO_portInit with valid parameters | EN_DIO_Error_T is returned as DIO_OK | Matches Expected Result | Pass
TC_DIO_006 | Test port write | 1. Call DIO_portInit with valid parameters 2. Call DIO_portWrite with a value of 0x55 and a mask of 0xFF (DIO_NO_MASK) | The specified port pins are set to 0x55 | Matches Expected Result | Pass
TC_DIO_007 | Test port toggle | 1. Call DIO_portInit with valid parameters 2. Call DIO_portWrite with a value of 0x55 and a mask of 0xFF (DIO_NO_MASK) 3. Call DIO_portToggle with a mask of 0xFF (DIO_NO_MASK) 4. Call DIO_portWrite with a value of 0xAA and a mask of 0xFF (DIO_NO_MASK) 5. Call DIO_portToggle with a mask of 0xFF (DIO_NO_MASK) | The specified port pins are toggled between 0x55 and 0xAA | Matches Expected Result | Pass
TC_DIO_008 | Re-Test with invalid data | Re-test cases from 1 to 7 with invalid data | Return DIO_ERROR | Matches Expected Result | Pass
EXI Driver
TC_EXI_001 | Test EXI enablePIE | 1. Call EXI_enablePIE with valid parameters (Correct interruptId and senseControl) | STD_OK is returned as u8 errorState | Matches Expected Result | Pass
TC_EXI_002 | Test EXI enablePIE | 1. Call EXI_enablePIE with invalid parameters (Incorrect interruptId or senseControl) | STD_NOK is returned as u8 errorState | Matches Expected Result | Pass
TC_EXI_003 | Test EXI disablePIE | 1. Call EXI_disablePIE with valid parameters (Correct interruptId) | STD_OK is returned as u8 errorState | Matches Expected Result | Pass
TC_EXI_004 | Test EXI disablePIE | 1. Call EXI_disablePIE with invalid parameters (Incorrect interruptId) | STD_NOK is returned as u8 errorState | Matches Expected Result | Pass
TC_EXI_005 | Test EXI intSetCallBack | 1. Call EXI_intSetCallBack with valid parameters (Correct interruptId and Valid Pointer) | STD_OK is returned as u8 errorState | Matches Expected Result | Pass
TC_EXI_006 | Test EXI intSetCallBack | 1. Call EXI_intSetCallBack with invalid parameters (Incorrect interruptId or Null Pointer) | STD_NOK is returned as u8 errorState | Matches Expected Result | Pass
TIMER Driver
TC_TIMER_001 | Test timer0 & timer2 Init | 1. Call TMR_timer0NormalModeInit & TMR_timer2NormalModeInit | The two timers working in the normal mode | Matches Expected Result | Pass
TC_TIMER_002 | Test timer0 delay function | 1. Call TMR_timer2Delay with deferent delay ranges | The desired delay is acheived | Matches Expected Result | Pass
TC_TIMER_003 | Test timer2 delay function | 1. Call TMR_timer0Delay with deferent delay ranges | The desired delay is acheived | Matches Expected Result | Pass
TC_TIMER_004 | Test timer0 & timer2 start | 1. Call TMR_timer0Start & TMR_timer2Start | The two timers start working in normal mode | Matches Expected Result | Pass
I2C Driver
TC_I2C_001 | Test TWI_init | 1. Call TWI_init | TWI module is initialized | Matches Expected Result | Pass
TC_I2C_002 | Test TWI_start | 1. Call TWI_start | TWI module send a start bit. | Matches Expected Result | Pass
TC_I2C_003 | Test TWI_write | 1. Call TWI_write | TWI module read a data/address . | Matches Expected Result | Pass
TC_I2C_004 | Test TWI_readWithAck | 1. Call TWI_readWithAck | TWI module read data with Ack. | Matches Expected Result | Pass
TC_I2C_005 | Test TWI_readWithNAck | 1. Call TWI_readWithNAck | TWI module read data with Not_Ack. | Matches Expected Result | Pass
TC_I2C_006 | Test TWI_stop | 1. Call TWI_stop | TWI module send a stop bit. | Matches Expected Result | Pass
SPI Driver
TC_SPI_001 | Test SPI send / receive | 1. Setup proteus simulation with SPI debugger 2. Setup MASTER loop to send numbers from 0 upwards 3. Setup SLAVE to echo what it recieves | Master recieves what was sent in the previous cycle | Matches Expected Result | Pass
TC_SPI_002 | Test SPI restart | Repeat case 1, adding a SPI_restart() every 8 transmissions | SPI debugger shows restarts, data resumes to be echoed successfuly | Matches Expected Result | Pass
TC_SPI_003 | Test SPI stop | Repeat case 1, but call SPI_stop() after 8 transmissions | No data is sent/recieved after 8 times as slave isn't shifting anything out SPI Debugger shows SPI inactive after 8 cycles | Matches Expected Result | Pass
UART Driver
TC_UART_001 | Test UART initialization | Call UART_initialization | UART peripheral is initialized with the configurations selected in the .config file | Matches Expected Result | Pass
TC_UART_002 | Test UART receiveByte | Call UART_receiveByte with valid parameters (Correct interruptionMode and Valid Pointer) | STD_OK is returned as u8 errorState | Matches Expected Result | Pass
TC_UART_003 | Test UART receiveByte | Call UART_receiveByte with invalid parameters (Incorrect interruptionMode or Null Pointer) | STD_NOK is returned as u8 errorState | Matches Expected Result | Pass
TC_UART_004 | Test UART receiveByteBlock | Call UART_receiveByte with valid parameters (Valid Pointer) | STD_OK is returned as u8 errorState | Matches Expected Result | Pass
TC_UART_005 | Test UART receiveByteBlock | Call UART_receiveByte with invalid parameters (Null Pointer) | STD_NOK is returned as u8 errorState | Matches Expected Result | Pass
TC_UART_006 | Test UART transmitByte | Call UART_transmitByte with valid parameters (Correct interruptionMode and transmitByte) | STD_OK is returned as u8 errorState | Matches Expected Result | Pass
TC_UART_007 | Test UART transmitByte | Call UART_transmitByte with invalid parameters (Inorrect interruptionMode or transmitByte) | STD_NOK is returned as u8 errorState | Matches Expected Result | Pass
TC_UART_008 | Test UART transmitString | Call UART_transmitString with valid parameters (Valid Pointer) | STD_OK is returned as u8 errorState | Matches Expected Result | Pass
TC_UART_009 | Test UART transmitString | Call UART_transmitString with invalid parameters (Null Pointer) | STD_NOK is returned as u8 errorState | Matches Expected Result | Pass
TC_UART_010 | Test UART RXCSetCallBack | Call UART_RXCSetCallBack with valid parameters (Valid Pointer) | STD_OK is returned as u8 errorState | Matches Expected Result | Pass
TC_UART_011 | Test UART RXCSetCallBack | Call UART_RXCSetCallBack with invalid parameters (Null Pointer) | STD_NOK is returned as u8 errorState | Matches Expected Result | Pass
TC_UART_012 | Test UART UDRESetCallBack | Call UART_UDRESetCallBack with valid parameters (Valid Pointer) | STD_OK is returned as u8 errorState | Matches Expected Result | Pass
TC_UART_013 | Test UART UDRESetCallBack | Call UART_UDRESetCallBack with invalid parameters (Null Pointer) | STD_NOK is returned as u8 errorState | Matches Expected Result | Pass
TC_UART_014 | Test UART TXCSetCallBack | Call UART_TXCSetCallBack with valid parameters (Valid Pointer) | STD_OK is returned as u8 errorState | Matches Expected Result | Pass
TC_UART_015 | Test UART TXCSetCallBack | Call UART_TXCSetCallBack with invalid parameters (Null Pointer) | STD_NOK is returned as u8 errorState | Matches Expected Result | Pass
HAL Module
BUZ Driver
TC_BUZ_001 | Test buzzer init | Call BUZZER_init() | The Buzzer module should be initialized | Matches Expected Result | Pass
TC_BUZ_002 | Test buzzer on | Call BUZZER_on() | The buzzer should be turned on | Matches Expected Result | Pass
TC_BUZ_003 | Test buzzer off | Call BUZZER_off() | The buzzer should be turned off | Matches Expected Result | Pass
MBTN Driver
TC_BTN_001 | Test Init | Call the MBTN_init passing the button configuration | Btn pins are set as inputs, enabling pullup resistor | Matches Expected Result | Pass
TC_BTN_002 | Test not pressed | Call getBtnState with button not pressed | function returns NOT_PRESSED | Matches Expected Result | Pass
TC_BTN_003 | Test short press | Call getBtnState with button pressed and released shortly | return is RELEASED | Matches Expected Result | Pass
TC_BTN_004 | Test long press/release | Call getBtnState with button pressed then after 2 seconds released | function breaks after 2 seconds exactly and returns LONG_RELEASED | Matches Expected Result | Pass
TC_BTN_005 | Test long press no release for 2s | Call getBtnState with button pressed then after more than 2 seconds released | function breaks after 2 seconds exactly and returns LONG_RELEASED | Matches Expected Result | Pass
LCD Driver
TC_LCD_001 | Test LCD Initialization | Call LCD_init() function. | The LCD module should be initialized and ready to display data. | Matches Expected Result | Pass
TC_LCD_002 | Test Sending Command | Call LCD_sendCommand() function with a valid command. | The command should be successfully sent to the LCD controller and executed. | Matches Expected Result | Pass
TC_LCD_003 | Test Sending Character | Call LCD_sendChar() function with a valid character. | The character should be displayed on the LCD screen. | Matches Expected Result | Pass
TC_LCD_004 | Test Sending String | Call LCD_sendString() function with a valid null-terminated string. | The string should be displayed on the LCD screen. If the character '\n' is encountered, the cursor should move to the beginning of the next line. | Matches Expected Result | Pass
TC_LCD_005 | Test Setting Cursor Position | Call LCD_setCursor() function with valid line and column values. | The cursor should be set to the specified line and column on the LCD screen. | Matches Expected Result | Pass
TC_LCD_006 | Test Storing Custom Character | Call LCD_storeCustomCharacter() function with a valid bitmap pattern and location. | The custom character should be successfully stored in the CGRAM of the LCD module. | Matches Expected Result | Pass
TC_LCD_007 | Test Clearing Display | Call LCD_clear() function. | The LCD screen should be cleared and the cursor should be returned to the home position (line 0, column 0). | Matches Expected Result | Pass
KPD Driver
TC_KPD_001 | Test KPD_initKPD | Call the KPD_initKPD | Rows Pins are set as Output, Columns Pins are set as Input (enabling pullup resistor) | Matches Expected Result | Pass
TC_KPD_002 | Test KPD_enableKPD | Call KPD_enableKPD | Rows Pins are set as Output (enable or re-enable KPD) | Matches Expected Result | Pass
TC_KPD_003 | Test KPD_disableKPD | Call KPD_disableKPD | Rows Pins are set as Input (disable KPD) | Matches Expected Result | Pass
TC_KPD_004 | Test KPD getPressedKey | Call KPD_getPressedKey with valid parameters (Valid Pointer) | STD_OK is returned as u8 errorState | Matches Expected Result | Pass
TC_KPD_005 | Test KPD getPressedKey | Call KPD_getPressedKey with invalid parameters (Null Pointer) | STD_NOK is returned as u8 errorState | Matches Expected Result | Pass
EEPROM Driver
TC_EEPROM_003 | Test Initializing the EEPROM | Call EEPROM_init function | The TWI module is initialized | Matches Expected Result | Pass
TC_EEPROM_001 | Test Writing on EEPROM | Call the EEPROM_writeByte function. | One byte is written inside the ext_memory | Matches Expected Result | Pass
TC_EEPROM_002 | Test Reading from EEPROM | Call EEPROM_readByte function | One byte is returned from the specific address | Matches Expected Result | Pass
APP Module
ATM ECU APP
TC_ATM_APP_001 | Inputs before trigger signal | Test all keypad keys and ENTER/0 Button before trigger signal | No action | Matches Expected Result | Pass
TC_ATM_APP_002 | Enter wrong PIN 3 times | Insert Card, then enter user pin 3 times wrong in a row | System lock, Alarm ON until reset | Matches Expected Result | Pass
TC_ATM_APP_003 | Enter Invalid PIN (pin length) | Try to enter invalid PIN length | No action, no more digits to be entered on LCD / System | Matches Expected Result | Pass
TC_ATM_APP_004 | Enter correct PIN | Insert Card -> Enter correct PIN number | System logs user in -> ask for transaction amount | Matches Expected Result | Pass
Card ECU APP
TC_CARD_APP_001 | PAN > 19 | Enter PAN that is more than 19 chars | Fail, Wrong PAN [Not in Valid Range] | Matches Expected Result | Pass
TC_CARD_APP_002 | PAN < 16 | Enter PAN that is less than 16 chars | Fail, Wrong PAN [Not in Valid Range] | Matches Expected Result | Pass
TC_CARD_APP_003 | PAN with alpha chars | Enter PAN with alphabetic characters | Fail, Wrong PAN [Non Numeric]" | Matches Expected Result | Pass
TC_CARD_APP_004 | Correct PAN | Enter correct PAN in Valid Range (16 -> 19) [Numeric] | Pass, PAN is saved successfully | Matches Expected Result | Pass
TC_CARD_APP_005 | PIN < 4 | Enter PIN number all numeric but less than 4 characters | Fail, Wrong PIN [Not 4 Digits] | Matches Expected Result | Pass
TC_CARD_APP_006 | PIN > 4 | Enter PIN number all numeric but more than 4 characters | Fail, Wrong PIN [Not 4 Digits] | Matches Expected Result | Pass
TC_CARD_APP_007 | PIN with alpha | Enter PIN number with correct length but with alphanumeric characters | Fail, Wrong PIN [Non Numeric] | Matches Expected Result | Pass
TC_CARD_APP_008 | Different confirmation PIN | Enter different PIN confirmation that the first PIN | Fail, Wrong PIN [Non Identical] | Matches Expected Result | Pass
TC_CARD_APP_009 | Correct PIN | Enter correct PIN 4 chars in length [Numeric] | Pass, Will ask for the Confirmation PIN | Matches Expected Result | Pass
TC_CARD_APP_010 | Correct PIN confirmation | Enter correct PIN 4 chars in length [Numeric and Identical to first PIN] | Pass, PIN is saved successfully | Matches Expected Result | Pass
User Stories
TC_ATM_APP_001 | Fraud Card | Insert a card that has no entry on the ATM database | System lock, FRAUD CARD message is displayed, Alarm ON until reset | Matches Expected Result | Pass
TC_USER_STR_002 | Stolen Card | Insert a card that has an entry in ATM DB but the card status is BLOCKED | System lock, STOLEN CARD message is displayed, Alarm ON until reset | Matches Expected Result | Pass
TC_USER_STR_003 | Max limit exceeded | Insert a valid card, try to make a transaction that is above the limit (5000.0) | Rejected, max limit exceeded, reset to insertion of amount again | Matches Expected Result | Pass
TC_USER_STR_004 | Insufficient fund | Insert a valid card, try to make a transaction that is not above the limit but the user account doesn't have enough funds for it | Rejected, insufficient exceeded, reset to insertion of amount again | Matches Expected Result | Pass
TC_USER_STR_005 | Approved Transaction | Insert a valid card, try to make a transaction that is not above the limit and the user account balance covers it | Approved, Rem. balance is: xxxx, Ejecting card, reset system | Matches Expected Result | Pass